## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Green
Contoso, Ltd.
Riku Nakano
Project start date: | 2024-01-08 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | January | [13 empty] | February | [27 empty] | March
 | time axis 2024-01-21 to 2024-03-16
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-01-21 to 2024-03-16
Project development
Project charter |  | 25% | 2024-01-11 | 3
Research |  |  | 2024-01-16 | 1
Projections |  | 50% | 2024-01-08 | 10
Stakeholders |  |  | 2024-01-31 | 1 | bar: 2024-01-31
Review |  | 10% | 2024-01-17 | 6
Contracts
Proposals |  | 60% | 2024-01-17 | 13
Document review |  | 50% | 2024-01-18 | 9
Bid date |  | 33% | 2024-01-26 | 11
Award date |  |  | 2024-02-04 | 1 | bar: 2024-02-04
Finalize |  |  | 2024-02-05 | 24
Design
Feasibility study |  |  | 2024-01-26 | 4
Submit permit applications |  |  | 2024-01-30 | 14
Design proposal |  |  | 2024-02-15 | 6
Materials |  |  | 2024-02-28 | 3
Equipment |  |  | 2024-02-20 | 19
Testing
Environment |  |  | 2024-02-17 | 15
System test |  |  | 2024-02-09 | 5
Issues/bugs |  |  | 2024-03-31 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2024-01-08 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | January | [13 empty] | February | [27 empty] | March
 | time axis 2024-01-21 to 2024-03-16
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-01-21 to 2024-03-16
Title 1
Task 1 |  | 25% | 2024-01-11 | 3
Task 2 |  |  | 2024-01-16 | 1
Task 3 |  | 50% | 2024-01-08 | 10
Task 4 |  |  | 2024-01-31 | 1 | bar: 2024-01-31
Task 5 |  | 10% | 2024-01-17 | 6
Title 2
Task 1 |  | 60% | 2024-01-17 | 13
Task 2 |  | 50% | 2024-01-18 | 9
Task 3 |  | 33% | 2024-01-26 | 11
Task 4 |  |  | 2024-02-04 | 1 | bar: 2024-02-04
Task 5 |  |  | 2024-02-05 | 24
Title 3
Task 1 |  |  | 2024-01-26 | 4
Task 2 |  |  | 2024-01-30 | 14
Task 3 |  |  | 2024-02-15 | 6
Task 4 |  |  | 2024-02-28 | 3
Task 5 |  |  | 2024-02-20 | 19
Title 4
Task 1 |  |  | 2024-02-17 | 15
Task 2 |  |  | 2024-02-09 | 5
Task 3 |  |  | 2024-03-31 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
CSC3002: Multi-task learning of objects and parts
Student: Hailin Weng
Supervisor: Barry Devereux
Project start date: | 2023-10-06 | [10 empty] | Scrolling increment: | [5 empty] | 50
Milestone marker: | 1 |  |  |  | November | [6 empty] | December | [34 empty] | January
 | time axis 2023-11-25 to 2024-01-19
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-11-25 to 2024-01-19
Foundation
Machine Learning |  | 70% | 2023-10-06 | 100
Deep Learning |  | 40% | 2023-10-09 | 97
Computer Vision |  | 30% | 2023-10-11 | 95
Implementation
AlexNet (Pytorch) |  | 100% | 2023-10-13 | 90
Property Norms |  | 80% | 2023-10-23 | 83
Develop (Solution)
My own CNN (Project) |  | 10% | 2023-11-09 | 66
Project Description, Solution Approach and Work Plan |  | 100% | 2024-01-01 | 13
Demo |  |  | 2024-01-12 | 1 | bar: 2024-01-12
Dissertation
Final Dissertation |  |  | 1/13/2024 | 91
Demonstration |  |  | 2024-04-13 | 1